## Template
Index
Slno | Facility Name | Client Name | Date of given | Floor | Area/location | Catagory | Check points | Status (Open/Close) | Snagpoints | Priority | Ref.images | Ref.images | Date of Closed | Closed Images | Vendor name | Project Spoc | Transition spoc
1 | [5 empty] | Electrical | Is all Lights installed and working condition as per the drawings/Design/RCP |  |  | Medium
2 | [5 empty] | Electrical | Is Emeregency lights is available and working condition for all areas as per drawing/Design with identification |  |  | High
3 | [5 empty] | Electrical | Is all lights installed without any loose connection or Hanging wires with allignment |  |  | Medium
4 | [5 empty] | Electrical | Is all area Lights installed without darkness of area |  |  | Medium
5 | [5 empty] | Electrical | Is Lux level is achiving as per the design/Draiwings (Standard to be done ) |  |  | Medium
6 | [5 empty] | Electrical | Is Lighining sensors installed in each enclose room with good working condition |  |  | Medium
7 | [5 empty] | Electrical | Is client logo lights good working condition |  |  | Medium
8 | [5 empty] | Electrical | Is proper support is provided in 2x2 Lights install in Grid ceiling |  |  | Medium
9 | [5 empty] | Electrical | Is all temparary lights and cablesis removed |  |  | Medium
10 | [5 empty] | Electrical | Is lights should not installed different type (like Cool,Warm,Milky white like ) |  |  | Medium
11 | [5 empty] | Electrical | Is all Raw power, UPS power and EL DB is installed and working conditon as per the SLD/design/drawings |  |  | Medium
12 | [5 empty] | Electrical | Is all Raw and UPS power DB proper addressing/Nomenclature is installed |  |  | Medium
13 | [5 empty] | Electrical | Is the DB frame and door properly fixed without any damages and easily access the DB without any obstuction |  |  | Medium
14 | [5 empty] | Electrical | Is UPS industrial socket is provided in Hub room |  |  | High
15 | [5 empty] | Electrical | Is all UPS and Raw power DB's are connected to earthing and value should be less then 3 ohms |  |  | High
16 | [5 empty] | Electrical | If Dedicated client earthpit to be check if anthing is there |  |  | High
17 | [5 empty] | Furniture | Is all conduits is running in Raceway/Cable tray |  |  | Medium
18 | [5 empty] | Electrical | Is Loose wire should not be Hanging condition in floor |  |  | Medium
19 | [5 empty] | Electrical | Is UPS point is available for wi-fi router , Biometeric system,RFS system,VMS ,Projector , TV all meeting rooms |  |  | Medium
20 | [5 empty] | Electrical | Is floor wise meter reading installed withdual source energy meters connected properly & DG sensing cable connection to meter |  |  | High
21 | [5 empty] | Electrical | Is Raw power scoket is provided in Workstation area, common area for Vaccum machine purpose |  |  | Medium
22 | [5 empty] | Electrical | Is the Electrical shock proof rubber mats available in electrical room |  |  | Medium
23 | [5 empty] | Electrical | Is Workstation and Meeting room Popup boxed properly fixed without any Hanging condition |  |  | Medium
24 | [5 empty] | Electrical | Is UPS power provision is provided AHU fire Damper control panel |  |  | High
25 | [5 empty] | Electrical | Is the Gland with earthing is installed in all cable wherever entry to DB/Panel/MCB's |  |  | Medium
26 | [5 empty] | Electrical | Is All electrical Cable Incoming/ Outgoing tagging is done |  |  | Medium
27 | [5 empty] | Electrical | Is all Electrical standard awarness signgages installed (415V danger sign need to be placed LT panel and DB) |  |  | Medium
28 | [5 empty] | Electrical | Is Emergency rescue & first aid procedure installed at LT room (local language, engish or hindi) |  |  | Medium
29 | [5 empty] | Electrical | Is the Raised floor supporting rod (for structure) need to be connected to earthing plate. (As per CDCP & Safety guidelines) |  |  | Medium
30 | [5 empty] | Electrical | Is Body of server rack ,False flooring and other equipment to be connected to earthing stips |  |  | High
31 | [5 empty] | Electrical | Is A/c outdoor unit area isolator box is 65/68 model-water/weather proof provided |  |  | Medium
32 | [5 empty] | Electrical | Is All Exhuast /Fresh air Fan switches control install in accessible height |  |  | Medium
33 | [5 empty] | Electrical | Is ferrule is provided end to end with necessary power circuit numbering for DB's |  |  | Medium
34 | [5 empty] | Interior | Is All extra thread rods trimmed in all supports (tray, copper pipe and etc...) |  |  | Medium
35 | [5 empty] | Hvac | Is All ac units /Duct is installed as per the drawings |  |  | Medium
36 | [5 empty] | Hvac | Is Fresh/exhuast system provision is done as per the drawing |  |  | High
37 | [5 empty] | Hvac | Is all Ac remotes has been fixed in the cabins for all indoor units |  |  | Medium
38 | [5 empty] | Hvac | Is all Supply and return Diffueser installed and identification is done |  |  | Medium
39 | [5 empty] | Hvac | Is air Balancing is completed and achiving CFM as per Design |  |  | High
40 | [5 empty] | Hvac | Is all the area's Temperature is achiving 21' to 23 degree |  |  | High
41 | [5 empty] | Hvac | Is Co2 Level achiving below 1000PPM all the area |  |  | High
42 | [5 empty] | Hvac | is trap door is available for Ac units where ever requried with provion for access for services |  |  | High
43 | [5 empty] | Hvac | Is the DB Level is achiveing all area below 45 DB |  |  | High
44 | [5 empty] | Hvac | Is Ac unit timer is available for Dual/Standy by units |  |  | High
45 | [5 empty] | Hvac | Is Reception,Cafeteria and Coworking area Ac unit Timer to be install |  |  | High
46 | [5 empty] | Hvac | Is All Critical room working and stand by unit installed (ISP(Hub room),UPS..Any other ) |  |  | High
47 | [5 empty] | Hvac | Is ensure no water Leakage from the ac units /Drain pipe with U trap |  |  | Medium
48 | [5 empty] | Hvac | Is Exhuast fan is installed in Pantry area |  |  | Medium
49 | [5 empty] | Hvac | Is near outdoor unit proper condensation is Happening (Temp <35) |  |  | Medium
50 | [5 empty] | Hvac | Is VCD availability for all the duct branches with Open/Close signages (stickers ) |  |  | Medium
51 | [5 empty] | Hvac | Is butterfly damper availability for AC inlet ducts |  |  | Medium
52 | [5 empty] | Hvac | Is Z (L) type Ducts installed for return air path in enclosed cabin |  |  | Medium
53 | [5 empty] | Hvac | Is indoor and outdoor names and Rubber pads and all Screws installed |  |  | Medium
54 | [5 empty] | Hvac | Is Ac outdoor units Condenser coil is good condition without any damages and body earthing to be connected |  |  | Medium
55 | [5 empty] | Hvac | Is Ac unit and drain pipe should not install above Electrical Panel (Server rack, Electrical panel and other Electriacal equipements) |  |  | High
56 | [5 empty] | Hvac | Is insulation of the duct to be installed inside the duct as per drawings |  |  | High
57 | [5 empty] | Hvac | Is Ac Unit trap door - inside -Accoustic needs to be done to controll the noise and all corner with support to be provided |  |  | Medium
58 | [5 empty] | Hvac | Is Canvas installed in ahu / duct mouth with Jip |  |  | Medium
59 | [5 empty] | Hvac | Is All Ac units swings is working condition without any abnormal noise |  |  | Medium
60 | [5 empty] | Hvac | Is Actuator is working condition ( Chill water & Fire damper ) |  |  | Medium
61 | [5 empty] | Hvac | Is Fire Damper is installed for Critical rooms in Centralised Ducts ruuning to Critical rooms |  |  | High
62 | [5 empty] | Hvac | Is Trap door is installed for Compact Cassette unit which is installed in gypsum ceiling |  |  | High
63 | [5 empty] | Rodent entry point | Is all opening should be closed which is made for Fresh air ducts , Exhuast dusts and copper pipe entry with same colour of the painting and water proof |  |  | Medium
64 | [5 empty] | Hvac | Is Cowl Pices with Mesh for the Fresh/Exhuast ducts in Outside installed to rain water should not entry |  |  | High
65 | [5 empty] | Hvac | Is VFD is installed and working condition in AHU |  |  | Medium
66 | [5 empty] | Hvac | Is VFD/ AHU is working condition in Auto /manual mode |  |  | High
67 | [5 empty] | Hvac | Is AHU is running in Bypass mode without VFD |  |  | Medium
68 | [5 empty] | Hvac | Is AHU Filter is installed with good and clean |  |  | Medium
69 | [5 empty] | Hvac | Is AHU room neat and clean and running in Dust free condition |  |  | Medium
70 | [5 empty] | Hvac | Is AHU Fire Damper -Actuator installed with Fire control panel |  |  | High
71 | [5 empty] | Hvac | Is AHU -Chiller Inlet /outlet Pressure guage ,Thermoguage is installed |  |  | High
72 | [5 empty] | Hvac | Is AHU Thermostat is installed and connected with Balacing valve |  |  | High
73 | [5 empty] | Hvac | Is AHU -Chiller line Y stainer is installed in AHU Chiller inlet |  |  | High
74 | [5 empty] | Hvac | Is AHU -Chiller line Buttery valve is installed in inlet/outlet |  |  | High
75 | [5 empty] | Hvac | Is AHU -Chiller line BTU meter is installed and working condition |  |  | High
76 | [5 empty] | Hvac | Is AHU room Fresh air provision is available |  |  | High
77 | [5 empty] | Hvac | Is AHU room proper accoustic is installed |  |  | Medium
78 | [5 empty] | Hvac | Is Water Tap is available in AHU room for filter cleaning |  |  | Medium
79 | [5 empty] | Hvac | Is Drain trap is available for AC fiiter cleaning |  |  | Medium
80 | [5 empty] | Hvac | Is Rubber pads in installed below AHU |  |  | Medium
81 | [5 empty] | Hvac | Is FCU coil is good conditon without any damages |  |  | High
82 | [5 empty] | Hvac | Is AHU door limit switch is working condition |  |  | High
83 | [5 empty] | Hvac | Is inside AHU -Lights is installed and working condtion |  |  | Medium
84 | [5 empty] | Hvac | Is emergency Push button is installed |  |  | Medium
85 | [5 empty] | Hvac | Is Duct silencer/Sound attentuatore installed as per drawing |  |  | High
86 | [5 empty] | Hvac | Is AHU inside motor abnormal noise and belt tension and UV light availability and working condition |  |  | Medium
87 | 2026-01-30 |  |  |  |  | Hvac | Number of ODU and Total capacity of ODU to be mentioned |  |  | Medium
88 | [5 empty] | Fire Safety | Is Smoke Detector, speaker ,MCP and Hooter is installed as per the drawings including cabins with access hight |  |  | Medium
89 | [5 empty] | Fire Safety | Is all Smoker detector ,MCP, sprinkler and Hooter is working condition with proper addressing/Numbering |  |  | Medium
90 | [5 empty] | Fire Safety | Is amplifier system is working condition with all speaker and console without auto annocement |  |  | Medium
91 | [5 empty] | Fire Safety | Is Fire Exinguisher Suitable standard available, FE Pressure is proper level, detail card is available and security checking and signature done as per drawings |  |  | Medium
92 | [5 empty] | Fire Safety | Is kichan area K Type fire extingusher installed |  |  | Medium
93 | [5 empty] | Fire Safety | Is Fire panel -Loop card capacity checked as per detectors installed |  |  | Medium
94 | [5 empty] | Fire Safety | Is amplifier capacity to be checked and speaker quantity to be checked |  |  | High
95 | [5 empty] | Fire Safety | Is music system cable to be layed separatly for PA controller for cafeteria , Reception, common Pantry, lift lobby and Rest room |  |  | High
[6 empty] | Fire Safety | Is music system should not to be provided in the Sick room, FM cabins, Meeting/Training room, Critical rooms |  |  | High
96 | [5 empty] | Fire Safety | Is Fire exit signage installed as per the drawing |  |  | Medium
97 | [5 empty] | Fire Safety | Is Fire escape route plan is installed with emmergency contact number |  |  | Medium
98 | [5 empty] | Fire Safety | Is Panic bar and buzzer with the signage installed in the fire exit door |  |  | High
99 | [5 empty] | Fire Safety | Is Heat detector is installd in pantry & kitchen |  |  | High
100 | [5 empty] | Fire Safety | Is FAPA system genrarated report is available and recived |  |  | High
101 | [5 empty] | Fire Safety | Is Smoke Detector with RI is installed below False flooring in main Critical/server /HUb rooms |  |  | Medium
102 | [5 empty] | Fire Safety | Is Main Fire panel installed and working condition without fault condition |  |  | High
103 | [5 empty] | Fire Safety | Is all FAPA is system is connected Main Fire panel and working condition with Proper addressing |  |  | High
104 | [5 empty] | Fire Safety | Is PA system Floorwise, Zonal wise to be Provided |  |  | Medium
105 | [5 empty] | Fire Safety | Is Sprinkler is installed as per the RCP drawings |  |  | Medium
106 | [5 empty] | Fire Safety | Is all sprinkler line valves are open condtion |  |  | High
107 | [5 empty] | Fire Safety | Is Sprinkler line drain provision need to be check for drain out |  |  | Medium
108 | [5 empty] | Fire Safety | In Critical room area sprinkler line should not come |  |  | Medium
109 | [5 empty] | Fire Safety | As per NBC sprinklerline height from ceiling if 800 mm above means above upright sprinkler need to be installed |  |  | Medium
110 | [5 empty] | Fire Safety | Is Fapa Isolator module provided or not for safety pupose |  |  | Medium
111 | [5 empty] | Fire Safety | Is Keys and Lock is available in FHS door |  |  | Medium
112 | [5 empty] | Fire Safety | Is FHS is nozzle & hose is placed with acceeies |  |  | High
113 | [5 empty] | Fire Safety | Is Gas leakage detection system for gas bank and working condition in Cafeteria,kitchen |  |  | High
114 | [5 empty] | Fire Safety | Glands needs to be provide for Detectors and speakers |  |  | Medium
115 | [5 empty] | Fire Safety | FAPA panel cupboard glass door frosting needs to be done |  |  | Medium
116 | [5 empty] | Fire Safety | FAPA Integration required for Builder panel and Indiqube panel |  |  | High
117 | [5 empty] | Fire Safety | Is relly Module with grouping is provided or not for Future any integration, AHU room, Server room, Near Flow switches |  |  | High
118 | [5 empty] | Fire Safety | Integration requried for Access control system, Ac units and other system with working condition |  |  | Medium
119 | [5 empty] | Fire Safety | Is Fire proof door is installed in all critical rooms All Critical rooms |  |  | Medium
120 | 2026-01-30 |  |  |  |  | Fire Safety | Is Sprinkler bulb installed 79 in Kitchen and More Heat producing space |  |  | High
121 | [5 empty] | Network | Is provision is made for access control cable work in main entrance door |  |  | Medium
122 | [5 empty] | Network | Is EDR (emmergency Door reliver is available If access is installed |  |  | High
123 | [5 empty] | Network | Is magnetic system is working properly if access is provided and proper cable dressing |  |  | Medium
124 | [5 empty] | Network | Is access control reader is working |  |  | Medium
125 | [5 empty] | Network | Is Access control systtem integrated to Fire panel or not |  |  | High
126 | [5 empty] | Furniture | Is all Door is installed as per drawing and working condition with locks |  |  | Medium
127 | [5 empty] | Furniture | Is there is no noise from the door, alligned properly with all inges screws |  |  | High
128 | [5 empty] | Furniture | Is door gasket is installed to all glass meeting rooms |  |  | Medium
129 | [5 empty] | Furniture | Is Push and Pull sticker installed in all Door |  |  | Medium
130 | [5 empty] | Furniture | Is all the door handles are fixed properly with proper tightness |  |  | Medium
131 | [5 empty] | Furniture | Is Door stopper is installed in required places |  |  | Medium
132 | [5 empty] | Furniture | Is Automatic door bottom curtain is installed |  |  | High
133 | [5 empty] | Furniture | Is glass froasting is done or not as per the design |  |  | Medium
134 | [5 empty] | Furniture | Is Main door Client logos are installed |  |  | High
135 | [5 empty] | Furniture | Is Door Glass and aluminium frame scratches free condition |  |  | Medium
136 | [5 empty] | Furniture | Is All door keys is working condition and Handed over to FM/Client |  |  | High
137 | [5 empty] | Furniture | Is workstation and pedastal installed as per the Drawings/Design without damages |  |  | Medium
138 | [5 empty] | Furniture | Is the workstation glass partition is fixed firmly without any damages |  |  | High
139 | [5 empty] | Furniture | Is raceways lines are finished properly without any carpet hanging out |  |  | Medium
140 | [5 empty] | Furniture | Is Pedestal locks and keys are working properly and Handed over FM |  |  | Medium
141 | [5 empty] | Furniture | Is the cable manager is covered properly with proper Cable raceway |  |  | Medium
142 | [5 empty] | Furniture | Is chairs have been placed as per the standard |  |  | High
143 | [5 empty] | Furniture | Is Chair adjustment,wheels, Handrest are functioning properly without any damages |  |  | Medium
144 | [5 empty] | Furniture | Is Modestay panel is installed in - all Workstation |  |  | Medium
145 | [5 empty] | Furniture | Is all work station and meeting room vertical cable tray installed or not |  |  | High
146 | [5 empty] | Furniture | Is the Locks for Pantry storage and cupboard is provided |  |  | Medium
147 | [5 empty] | Furniture | Is Sharp edges needs to be nosing ( DB'S, Cainb cupboards, Pantry Cupboards and Table Corners ) |  |  | High
148 | [5 empty] | Furniture | Water dispensers should not keep on the floor carpet(work station area) |  |  | High
149 | [5 empty] | Network | Check the availability of the Data and Voice Port points as per the Drawings/Design |  |  | Medium
150 | [5 empty] | Network | Check the availability of LAN connection for all workstations. |  |  | Medium
151 | [5 empty] | Network | Check the availability of the Network port for the RFS system near rest room |  |  | High
152 | [5 empty] | Network | Lan connection availability for meeting rooms. |  |  | Medium
153 | [5 empty] | Network | Check the availability of loose wires |  |  | Medium
154 | [5 empty] | Network | Cable routing is done properly |  |  | Medium
155 | [5 empty] | Network | backbone cable is done from indiqube hub room |  |  | High
156 | [5 empty] | Network | Check the availability of LAN connection for printer |  |  | Medium
157 | [5 empty] | Network | Wifi lan cable available |  |  | Medium
158 | [5 empty] | Network | Wifi Router is installed and internet connectivity working |  |  | High
159 | [5 empty] | Network | All the network face plate with numbering need to be install properly with eary accessible condition as per drawing/standard |  |  | Medium
160 | [5 empty] | Network | CCTV in common area and client space if required |  |  | High
161 | [5 empty] | Network | Check the availability of Dummy's in Faceplate which is not using in the Faceplate |  |  | Medium
162 | [5 empty] | Network | Check if there is a provision given to connect the projectors from ceiling to floor |  |  | Medium
163 | [5 empty] | Network | HDMI cable needs to be lay from powerpoint to meeting table |  |  | Medium
164 | [5 empty] | Interior | Is all floor is even condition |  |  | High
165 | [5 empty] | Interior | Is carpet is firmly fixed without dust (before installed dust ) |  |  | Medium
166 | [5 empty] | Interior | Is raceways connectors are covered properly |  |  | High
167 | [5 empty] | Interior | Is the corner skirting if fixed properly without gap with rubber |  |  | Medium
168 | [5 empty] | Interior | Is carpet have been fixed properly at all corners without gaps |  |  | High
169 | [5 empty] | Interior | Is floor tiles are fixed properly without Damaged and same colour Including False flooring tiles |  |  | High
170 | [5 empty] | Interior | Is transition profile has been fixed in required places |  |  | Medium
171 | [5 empty] | Interior | Is Lvt tiles layed properly without any undulation |  |  | Medium
172 | [5 empty] | Interior | Is Grouting is completed for all floor Tiles done or not and hallow sound coming or nor to be check |  |  | High
173 | [5 empty] | Interior | Is there is any seepage and water leakages found in the ceiling |  |  | High
174 | [5 empty] | Interior | Is the All wall painting is done properly |  |  | Medium
175 | [5 empty] | Interior | Is wall papers have been fixed neatly |  |  | Medium
176 | [5 empty] | Cleaning | Is no paint stains in the wall paper |  |  | Medium
177 | [5 empty] | Interior | Is ensuring that there is no crack in the wall |  |  | Medium
178 | [5 empty] | Rodent entry point | Is all Holes has been closed in Wall and Is all rodent entry point is closed |  |  | High
179 | [5 empty] | Interior | Is all False ceiling tiles are fixed properly without stains with proper support |  |  | Medium
180 | [5 empty] | Interior | Is all pipes and fixtures have been painted as per the ceiling colour |  |  | Medium
181 | [5 empty] | Interior | Is grid ceiling support is provided |  |  | High
182 | [5 empty] | Interior | Is facade Glass is good condition with clean without any damages |  |  | High
183 | [5 empty] | Interior | Is found there is any leakage from the façade |  |  | High
184 | [5 empty] | Interior | Is all Openable Facade windows have been locked with proper Lock |  |  | High
185 | [5 empty] | Interior | Is Façade bottom partition to be close floor to floor (Fire sealent ) |  |  | Medium
186 | [5 empty] | Interior | Is Façade glass installed all area and same type of glass installed with cleaning without gaps |  |  | Medium
187 | [5 empty] | Interior | Is Gaps should not available in door to frames |  |  | Medium
188 | [5 empty] | Interior | Is the Blinds for window and required place with proper roller is installed |  |  | Medium
189 | [5 empty] | Interior | Is all blinds are functioning properly |  |  | Medium
190 | [5 empty] | Interior | Is Glass writing board if fixed properly properly without any Damaged in all enclosed cabin |  |  | High
191 | [5 empty] | Interior | Is Accoustic is installed all in cabin as per the design without any gaps |  |  | Medium
192 | [5 empty] | Interior | Is Sound proff cabin to cabin to be checked |  |  | High
193 | [5 empty] | Interior | Is Client Cafeteria or Terrace Balcony area drain line needs to check |  |  | Medium
194 | [5 empty] | Parking | Is Parking marking with Numbering is done |  |  | High
195 | [5 empty] | Interior | Is bundwall is avabile in cafeteria area rain water doesn't enter to inside building |  |  | Medium
196 | [5 empty] | Interior | Is Drain provision provided in the pantry area for coffee machine with drainline |  |  | High
197 | [5 empty] | Interior | Is pillar gaurd installed in all columns |  |  | Medium
198 | [5 empty] | Furniture | Is List available for Indiqube scope and Client scope details |  |  | High
199 | [5 empty] | Signages | Is Client name add in the VMS |  |  | High
200 | [5 empty] | Signages | Is Rest room signages to be installed |  |  | High
201 | [5 empty] | Signages | Is Client Name is installed in client Directory board |  |  | High
202 | [5 empty] | Parking | Is parking signages with allocation |  |  | High
203 | [5 empty] | Cleaning | Is all are Deep cleaning is completed |  |  | Medium
204 | [5 empty] | Cleaning | Is All above ceiling Height cleaning is done |  |  | Medium
205 | [5 empty] | Cleaning | Is All Project unused and unwanted material is cleares in client space and client Parking area |  |  | High
206 | [5 empty] | Landscapping | is Landscapping work is completed |  |  | High
207 | [5 empty] | Landscapping | Is Landscapping work - Amc is available status (Yes/No) (1 month - Free Warranty for client space) |  |  | High
208 | [5 empty] | Landscapping | Is all meteeing room Ceramic planter pot placed |  |  | Medium
209 | [5 empty] | Interior | Is Glass door and Partition glasses free from scratches |  |  | Medium
210 | [5 empty] | Interior | Is all Chinna table and indiqube branding is done from Asset team |  |  | Medium
211 | [5 empty] | Network | Ensure all client space/common area access control access - access card needs to be provided Facility/Security if dedicated security is not available |  |  | High
212 | [5 empty] | Service | Is all service to be ensure as per the serivce subrication |  |  | High
213 | [5 empty] | Service | Is water service is available |  |  | Medium
214 | [5 empty] | Service | Is Pestcontrol is service done or not |  |  | High
215 | [5 empty] | Electrical | UPS load to be checked in UPS - After client onboarding load to be ensure mention here |  |  | High
216 | [5 empty] | Electrical | Thermography Testing to be done By the electrical vendors after the client Onboarding checklist |  |  | High
217 | [5 empty] | Interior | As per Final approval Layout all asset ,losse furniture and designer Elements to be install |  |  | Medium
218 | [5 empty] | Interior | Check the all cabins duster holder needs to be install without Damages |  |  | Medium
219 | 2025-06-16 |  |  |  |  | Electrical HOD | Electrical As built drawings, Warranty certificates, Lux level report , commissioing report to be submits |  |  | High
220 | 2025-06-16 |  |  |  |  | Hvac HOD | Hvac As built drawings, Warranty certificates, Co2, CFM level report , commissioing report to be submits |  |  | High
221 | 2025-06-16 |  |  |  |  | Fire Safety HOD | Hvac As built drawings, Warranty certificates, system genarated report , commissioing report to be submits |  |  | High
222 | 2025-06-16 |  |  |  |  | Network HOD | Network As built drawings, Warranty certificates, fluke test report , commissioing report to be submits |  |  | High
223 | 2025-06-16 |  |  |  |  | Electrical | Ensure Electrical demo activity is completed and mail has been shared to FM |  |  | High
224 | 2025-06-16 |  |  |  |  | Hvac | Ensure Hvac demo activity is completed and mail has been shared to FM |  |  | High
225 | 2025-06-16 |  |  |  |  | Fire Safety | Ensure FAPA demo activity is completed and mail has been shared to FM |  |  | High
226 | 2025-07-03 |  |  |  |  | Cleaning | Ensure cleaning is completed inside the Fire shaft,Plumbing shaft and Electrical shaft |  |  | High
227 | 2025-07-03 |  |  |  |  | Electrical | Ensure Meggar testing is done for cables |  |  | High